# Tender Preparation (HL Draft)

# Intertrade Ireland – AI for SMEs (All-Island) Research

February 2026

# Draft Tender Response

# AC-1: Approach to analysing the current AI capability landscape across both jurisdictions

Narrative framing

InterTrade Ireland’s unique mandate demands more than a literature review or jurisdiction-specific snapshot. Our approach to analysing the AI capability landscape is explicitly designed to deliver a genuinely all-island, SME-centred view, identifying where activity already exists, where gaps remain, and, critically, where InterTrade Ireland can add distinctive value without duplication.

Our consortium brings together two senior academic experts in AI and SME productivity (Queen’s University Belfast and Ulster University) alongside a delivery team with deep digital, AI and programme-management experience. This combination allows us to balance academic rigour, policy relevance, and operational realism from the outset.

Methodological Approach

Systematic Landscape Mapping and Evidence Review

We will undertake a structured, four-layer mapping of the AI capability landscape across Northern Ireland and Ireland:

- Policy and Strategy Layer
We will review national and regional strategies relating to AI, digitalisation, productivity, skills and enterprise development. Each document will be analysed using a consistent framework capturing objectives, target SME segments, delivery mechanisms, and stated productivity ambitions.

- Delivery and Intervention Layer
We will map existing AI-related supports available to SMEs, including grant schemes, advisory programmes, innovation centres, pilots and testbeds. Each intervention will be assessed for SME accessibility, scale, sectoral relevance, and maturity.

- Research and Insight Layer
Existing AI and SME productivity research will be reviewed and categorised to identify areas of robust evidence, fragmented insight, and clear gaps requiring new primary research.

- Regulatory and Operating Context Layer
We will examine the practical implications for SMEs operating under dual UK/EU regulatory regimes, focusing on AI governance, data protection, procurement, and liability, particularly for cross-border trading SMEs.

All findings will be collated in an AI Capability and Support Mapping Matrix, enabling systematic identification of:

- Duplication across initiatives

- Under-served SME segments or sectors

- Opportunities for coordination or rationalisation

- Areas where InterTrade Ireland’s all-island role provides unique leverage

Early Stakeholder Validation

To ensure accuracy and relevance, we will conduct early scoping interviews with InterTrade Ireland and selected stakeholders across both jurisdictions (enterprise agencies, delivery partners, innovation centres). This validation step ensures our mapping reflects operational reality and allows refinement of the research focus before primary fieldwork begins.

In parallel, we will engage with established SME intermediary networks, including InterTrade Ireland-supported businesses, Invest NI and Enterprise Ireland client networks, relevant trade bodies, local chambers of commerce, and professional services networks. This will support validation of the landscape assessment, ensure coverage of sector-specific initiatives that may not be captured through desk research alone, and provide early insight into how SMEs experience the current AI support ecosystem in practice.

Supplementary Narrative Analysis

To strengthen triangulation, we will apply light-touch corpus linguistic analysis to a curated corpus of policy and SME-focused AI publications. This will help identify dominant narratives, recurring themes, and perception gaps across jurisdiction, supporting a more nuanced interpretation of the landscape.

Value to InterTrade Ireland

This approach ensures InterTrade Ireland receives not just a map of “what exists”, but a clear diagnosis of where and how it can act differently and more effectively, as a connector, coordinator and catalyst across the island.

# AC-2: Approach to evaluating SME productivity and competitiveness gains from AI

Narrative framing

AI adoption is only meaningful insofar as it delivers measurable improvements in SME productivity and competitiveness. Our approach deliberately moves beyond headline adoption rates to examine how, where and to what extent AI and wider digital tools are translating into economic value for SMEs.

Drawing on our academic expertise in SME productivity and our practical experience delivering digital transformation programmes, we place productivity outcomes, not technology, at the centre of the analysis.

Methodological Approach

Productivity-led analytical framework

We will assess AI-enabled productivity across four dimensions:

- Cost efficiency (labour, error reduction, rework)

- Throughput and speed (cycle times, responsiveness)

- Quality and consistency (compliance, defect rates)

- Growth enablement (scalability, market access, service expansion)

This framework will be applied consistently across sectors and jurisdictions.

SME AI Adoption Maturity Model

We will classify SMEs using a structured AI Adoption Maturity Model, distinguishing between:

- Awareness and experimentation

- Tactical or isolated adoption

- Process-embedded adoption

- Organisation-wide, transformational use

This allows clear differentiation between superficial experimentation and productivity-enhancing transformation, a key requirement of this study.

Primary Data Collection

We will gather SME-level evidence through a multi-channel engagement strategy:

- Structured SME survey, capturing adoption levels, use cases, perceived productivity impacts, and constraints via Qualtrics. Survey data will be managed and analysed using SPSS, enabling robust descriptive analysis and segmentation by sector, size and jurisdiction.

- The SME survey will be distributed through trusted intermediary networks, including InterTrade Ireland, Invest NI and Enterprise Ireland client networks, trade associations, local chambers of commerce, and professional services networks. This approach maximises reach and response rates, supports sectoral diversity, and reduces sampling bias by engaging SMEs beyond those already highly active in digital or innovation programmes.

- Targeted digital outreach, including paid LinkedIn promotion, to engage SMEs beyond existing support networks and avoid sampling bias.

- In-depth SME interviews, providing qualitative insight into decision-making, before-and-after productivity impacts, and lessons learned.

- Qualitative interview data will be coded and analysed using NVivo, ensuring systematic identification of recurring themes and patterns.

Sector-specific Analysis

Findings will be analysed by sector to identify:

- High-potential AI use cases

- Sectors where adoption is lagging despite strong productivity opportunity

- Misalignment between current interventions and sector-specific needs

Value to InterTrade Ireland

This approach equips InterTrade Ireland with clear, evidence-based insight into where AI delivers real economic value, enabling more targeted and impactful support for SMEs across the island.

# AC-3: Approach to identifying barriers, enablers and international benchmarking

Narrative framing

Understanding why SMEs struggle, or succeed, with AI adoption is essential to designing effective interventions. Our approach combines SME-level evidence, system-level analysis, and selective international benchmarking to identify practical, addressable barriers and enablers.

Methodological approach

Barrier and Enabler Framework

Barriers and enablers will be analysed across five dimensions:

- Skills, leadership capability and confidence

- Cost, risk and ROI uncertainty

- Data readiness and systems maturity

- Regulatory and compliance complexity

- Awareness and accessibility of supports

These will be tested and quantified through SME surveys (Qualtrics/SPSS) and explored in depth through interviews (NVivo).

To support candid discussion of perceived risks, confidence gaps and regulatory concerns, qualitative interviews will be facilitated where possible through trusted intermediary networks, including trade bodies, chambers of commerce and professional services networks. Leveraging these trusted relationships enables SMEs to speak openly about barriers they may be reluctant to articulate through formal surveys alone, strengthening the depth and reliability of findings.

System-level Assessment

For each barrier, we will:

- Map existing supports and enablers

- Assess their design and accessibility from an SME perspective

- Identify points of friction, under-utilisation or misalignment

This ensures recommendations focus on improving effectiveness, not increasing complexity.

International Benchmarking

We will benchmark findings against comparable international jurisdictions with strong SME bases and active AI adoption policies. Benchmarking will focus on transferable practices, such as:

- SME-focused skills interventions

- De-risking mechanisms for AI investment

- Demand-side innovation policies

International examples will be assessed for relevance to the all-island context and compatibility with UK/EU regulatory environments.

Supplementary Narrative Analysis

Python/R-based lexicographic analysis will support identification of perception gaps between policy narratives and SME sentiment, strengthening interpretation of barriers linked to trust, confidence and awareness.

Value to InterTrade Ireland

This evidence-driven approach enables InterTrade Ireland to target root causes, not symptoms, and to advocate confidently for interventions grounded in both local evidence and international practice.

# AC-4: Approach to examining the public sector as a driver of SME innovation

Narrative Framing

The public sector has a powerful but under-utilised role as a demand-side driver of SME innovation. Our approach examines how procurement, open calls and pilot programmes can act as practical levers to stimulate AI adoption and capability-building among SMEs.

Methodological Approach

Demand-side Assessment Framework

Public sector mechanisms will be assessed against:

- SME accessibility and administrative burden

- Risk allocation and contract structure

- Time to decision and payment

- Learning and capability-building value

- Pathways from pilot to scaled adoption

Evidence Gathering

We will draw on:

- Review of existing procurement and innovation programmes

- Interviews with SMEs that have participated (or attempted to participate)

- Interviews with commissioning bodies and programme managers

This dual perspective ensures identification of both structural barriers and practical improvements.

International Comparison

Relevant international demand-side innovation models will be reviewed, focusing on:

- SME-friendly procurement

- Phased pilots and test-and-learn approaches

- Clear routes from pilot to market

Findings will be translated into implementable recommendations for the all-island context.

Value to InterTrade Ireland

This analysis positions InterTrade Ireland to influence and shape demand-side mechanisms, strengthening SME participation and accelerating AI capability development.

# AC-5: Approach to developing clear, specific and actionable recommendations

Narrative Framing

Recommendations are the bridge between insight and impact. Our approach ensures all recommendations are evidence-based, clearly owned, policy-aligned and practically deliverable, reinforcing InterTrade Ireland’s distinctive all-island role.

Methodological Approach

Structured Synthesis

Evidence from all phases will be synthesised using:

- The productivity framework

- The AI adoption maturity model

- Barrier and enabler analysis

This ensures coherence and traceability from evidence to recommendation.

Recommendation Architecture

Recommendations will be organised using a three-tier ownership model:

- Actions InterTrade Ireland can lead directly

- Areas for influence and policy advocacy

- Collaborative all-island interventions

Each recommendation will include:

- Objective and rationale

- Evidence base

- Lead and supporting actors

- Indicative timeframe

- Expected productivity or competitiveness impact

Stakeholder Validation

Interim findings and draft recommendations will be sense-checked with InterTrade Ireland, delivery partners and representative SME networks, including trade bodies, chambers of commerce and professional services networks. This ensures recommendations are grounded in delivery reality, aligned with existing support structures, and capable of being implemented through established networks rather than creating parallel or duplicative mechanisms.

Policy Alignment

All recommendations will be explicitly aligned to:

- Programmes for Government

- National AI strategies

- InterTrade Ireland’s Corporate Plan and strategic priorities

Value to InterTrade Ireland

The result will be a clear, actionable roadmap enabling InterTrade Ireland to act decisively, complementing existing activity, avoiding duplication, and strengthening SME productivity and competitiveness across the island.

# Operational Research Design

To ensure findings are robust, representative and deliverable within the project timeframe, the research will be underpinned by a clearly bounded operational design combining primary and secondary evidence.

Primary SME evidence will include:
A structured SME survey targeting approximately 300-500 responses across Ireland, segmented by sector, firm size and jurisdiction. Distribution will be supported through InterTrade Ireland and partner networks, supplemented by targeted digital outreach to mitigate sampling bias.

30–40 in-depth SME interviews, purposively sampled to reflect different levels of AI adoption maturity (from early experimentation to transformational use) and sectoral contexts.

Stakeholder evidence will include:

15–20 interviews with enterprise agencies, policy stakeholders, innovation centres, public sector bodies and representative organisations across both jurisdictions.

Secondary and documentary analysis will include:
Review of approximately 80–120 policy, research and industry publications, forming the basis for landscape mapping and supplementary narrative analysis.
Selective international benchmarking against 4–6 comparable jurisdictions, focused on transferable practices relevant to SME AI adoption and productivity.

This design ensures sufficient depth and coverage to support evidence-based conclusions, while remaining proportionate to the study’s objectives and budget.

# Academic Leadership and Contribution

The research will be delivered through a close collaboration between the core delivery team and two senior academic specialists, who will act as AI and SME Adoption and Productivity Co-Leads for the project. This joint leadership model ensures analytical rigour, balance across jurisdictions, and strong alignment between AI adoption dynamics and SME productivity outcomes.

Academic Co-Leads will retain intellectual independence in interpretation of findings, with conclusions grounded in the evidence generated through the agreed methodology.

Queen’s University Belfast (QUB) – AI and SME Adoption and Productivity Co-Lead
The QUB academic partner will co-lead the development of the SME productivity and competitiveness framework underpinning the study, working jointly on the design of the AI adoption maturity model. They will co-design the SME survey instrument, advise on productivity and performance indicators, and contribute to interpretation of quantitative findings to ensure analytical robustness and policy relevance.

Ulster University (UU) – AI and SME Adoption and Productivity Co-Lead
The UU academic partner will co-lead development of the AI adoption and maturity framework, working jointly on linking adoption stages to measurable productivity and competitiveness outcomes. They will contribute to international benchmarking, support analysis of system-level barriers and enablers, and co-author synthesis sections of the final report.

Both academic Co-Leads will participate in interim findings reviews, provide peer review of draft outputs, and support alignment of findings with current research and policy debates across both jurisdictions, ensuring a consistent and high-quality analytical narrative throughout the study.

# Delivery Effort and Cost Assumptions

The project has been costed to ensure sufficient resource is allocated to primary data collection, analysis, synthesis and stakeholder engagement, while remaining proportionate to the overall budget and six-month timeframe.

Indicative role allocation is set out below:

| Role. | Indicative Day Rate. | Estimated Days. | Subtotal. |
| --- | --- | --- | --- |
| Project Director. | £750 | 22 | £16,500 |
| AI & Digital Adoption Lead. | £700 | 24 | £16,800 |
| Research Analyst (Quant & Qual). | £550 | 30 | £16,500 |
| Policy & Stakeholder Engagement Lead. | £650 | 22 | £14,300 |
| Report Writing & Synthesis Lead. | £600 | 30 | £18,000 |
| SUBTOTAL |  |  | £82,100 |

Direct Research and Engagement Costs

Direct costs have been explicitly provisioned to ensure robust SME engagement and high-quality data capture. These include a dedicated survey platform licence (Qualtrics) to support structured data collection and management, and a ring-fenced budget for paid digital outreach to ensure adequate reach and representation across the SME population, including firms not currently engaged with public support programmes.

Additional provision is made for transcription and qualitative data processing, and for stakeholder engagement and dissemination activity. These costs are included within the overall budget envelope to ensure the study can be delivered to the required depth and quality without reliance on unfunded scope expansion.

| Cost Item | Estimated Cost |
| --- | --- |
| Qualtrics survey platform licence & data management | £3,000 |
| Paid digital advertising & targeted outreach to SMEs | £5,000 |
| Transcription & qualitative data processing | £500 |
| Stakeholder engagement & dissemination activity | £950 |
| Subtotal – Direct Costs | £9,450 |

Total Estimated Project Costs: £91,550 (ex VAT)